## Overview
Backend Requirements - Credit Notes System
Document Version | 1.0
Last Updated | January 16, 2026
Summary
This document outlines the backend API requirements for the Credit Notes System and Credited Sales View functionality.
The frontend has been implemented and is ready for API integration.

## Database Schema
Database Schema Requirements
Table Name | CreditNotes
Column Name | Data Type | Constraints
Id | INT | PRIMARY KEY IDENTITY(1,1)
CreditNoteNumber | NVARCHAR(50) | UNIQUE NOT NULL
InvoiceId | INT | NOT NULL, FK to Sales
InvoiceNumber | NVARCHAR(50) | NOT NULL
CustomerId | INT | NULL
CustomerName | NVARCHAR(200) | NOT NULL
OriginalAmount | DECIMAL(18,2) | NOT NULL
CreditAmount | DECIMAL(18,2) | NOT NULL
Reason | NVARCHAR(MAX) | NOT NULL
Status | NVARCHAR(20) | NOT NULL DEFAULT 'pending'
ReverseStock | BIT | NOT NULL DEFAULT 0
ReverseSale | BIT | NOT NULL DEFAULT 1
Notes | NVARCHAR(MAX) | NULL
DocumentFileName | NVARCHAR(255) | NULL
DocumentFileUrl | NVARCHAR(500) | NULL
DocumentUploadedDate | DATETIME | NULL
CreatedDate | DATETIME | NOT NULL DEFAULT GETDATE()
ApprovedDate | DATETIME | NULL
ApprovedBy | NVARCHAR(100) | NULL
LastUpdated | DATETIME | NOT NULL DEFAULT GETDATE()

## API Endpoints
API Endpoints
Method | Endpoint | Description | Status
GET | /api/CreditNotes | Get all credit notes with filtering | Phase 1 - Critical
GET | /api/CreditNotes/{id} | Get specific credit note by ID | Phase 1 - Critical
POST | /api/CreditNotes | Create new credit note | Phase 1 - Critical
PATCH | /api/CreditNotes/{id} | Update existing credit note | Phase 2 - High Priority
DELETE | /api/CreditNotes/{id} | Delete credit note (pending only) | Phase 3 - Medium Priority
POST | /api/CreditNotes/{id}/upload | Upload PDF document | Phase 3 - Medium Priority
GET | /api/CreditNotes/{id}/download | Download credit note document | Phase 3 - Medium Priority
GET | /api/Sales | Get sales (with credit note filter) | Phase 1 - Critical
GET | /api/Sales/Credited | Get all credited sales | Phase 2 - High Priority

## Implementation Phases
Implementation Phases
Phase | Priority | Timeline | Tasks
Phase 1 | Critical | Week 1 | Create CreditNotes table, Implement GET/POST endpoints, Update Sales API
Phase 2 | High | Week 2 | Implement PATCH endpoint, GET /Sales/Credited, Stock/Sale reversal logic
Phase 3 | Medium | Week 3 | File upload/download, Filtering, DELETE endpoint
Phase 4 | Low | Week 4 | Audit logging, Pagination, Performance optimization, Security

## Testing Checklist
Testing Checklist
Category | Test Case | Status
Credit Notes API | Create credit note with valid invoice ID | Pending
Credit Notes API | Create credit note with invalid invoice ID (should fail) | Pending
Credit Notes API | Create credit note with amount > original (should fail) | Pending
Credit Notes API | Retrieve all credit notes | Pending
Credit Notes API | Retrieve single credit note by ID | Pending
Credit Notes API | Filter credit notes by status | Pending
Credit Notes API | Update credit note status to approved | Pending
Credit Notes API | Cannot update completed credit note | Pending
Credit Notes API | Delete pending credit note | Pending
Credit Notes API | Cannot delete approved credit note | Pending
Credit Notes API | Upload PDF document (valid) | Pending
Credit Notes API | Upload non-PDF file (should fail) | Pending
Credit Notes API | Upload file > 5MB (should fail) | Pending
Credit Notes API | Download credit note document | Pending
Stock Reversal | Approve credit note with reverseStock = true | Pending
Stock Reversal | Verify inventory quantities increased | Pending
Stock Reversal | Verify stock movement logged | Pending
Stock Reversal | Multiple items reversed correctly | Pending
Sale Reversal | Approve credit note with reverseSale = true | Pending
Sale Reversal | Verify sale marked as credited | Pending
Sale Reversal | Partial credit applied correctly | Pending
Sale Reversal | Full credit marks sale as reversed | Pending
Integration | Frontend displays credit notes from API | Pending
Integration | Create credit note end-to-end flow | Pending
Integration | Invoice search returns correct results | Pending
Integration | Auto-fill works when invoice selected | Pending
Integration | PDF upload/download works | Pending
Integration | Credited sales view displays correctly | Pending
Integration | Filtering and searching works | Pending

## Frontend Integration
Frontend Integration Points
Component | File Path | Purpose
Credit Notes Component | src/app/dashboard/sales/credit-notes/credit-notes.component.ts | Credit notes management
Credit Notes Template | src/app/dashboard/sales/credit-notes/credit-notes.component.html | Credit notes UI
Credit Notes Styles | src/app/dashboard/sales/credit-notes/credit-notes.component.scss | Credit notes styling
List Sales Component | src/app/dashboard/sales/list-sales/list-sales.component.ts | Sales list with credited view
List Sales Template | src/app/dashboard/sales/list-sales/list-sales.component.html | Sales list UI
Sales API Service | src/app/dashboard/sales/services/sales-api.service.ts | API integration service
Mock Data Lines to Replace
credit-notes.component.ts | Line 113 | getMockCreditNotes() -> API call to /CreditNotes
credit-notes.component.ts | Line 92 | getMockSales() -> API call to /Sales
list-sales.component.ts | Line 211 | Mock filter -> API call to /Sales/Credited